## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 2023-06-30 12:00
Group Number |  | 1 - Webshop
Participant 1 |  | Binh Duong Nguyen
Participant 2 |  | Duy Hiep Le
Participant 3 |  | Daniel Pfeifhofer
Participant 4 |  | Rafael Jeitler
Participant 5 |  | Elias Karner
Mentor |  | Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Group Orders | 2 | 2 | 0 | 1
2 | Shipping Map | 3 | 3 | 0 | 1
3 | Shipping Options | 3 | 3 | 0 | 1
4 | Shipping (sim) | 3 | 3 | 0 | 1
5 | Shipping Adress | 2 | 2 | 0 | 1
6 | Shipping Page Design | 2 | 2 | 0 | 1
7 | Orders Admin Page | 3 | 4 | 1 | 1
8 | Orders Admin Page Design | 2 | 2 | 0 | 1
9 | Expand Finance Overview Seller | 2 | 2 | 0 | 1
n | Dummy Data | 2 | 1 | -1 | 1
9 |  |  |  | 0 | 10 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol