## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2023-05-23 12:00
Group Number |  | 1 - Webshop
Participant 1 |  | Binh Duong Nguyen
Participant 2 |  | Duy Hiep Le
Participant 3 |  | Daniel Pfeifhofer
Participant 4 |  | Rafael Jeitler
Participant 5 |  | Elias Karner
Mentor |  | Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Navbar Update | 2 | 2 | 0 | 1
2 | Website Design Color | 2 | 2 | 0 | 1
3 | Shopping Cart Picture | 2 | 2 | 0 | 1
4 | Order Status Design | 2 | 2 | 0 | 1
5 | Order Status Functionality | 2 | 2 | 0 | 1
6 | Inventar Seller Angebote | 2 | 2 | 0 | 1
7 | Inventar Management Admin | 2 | 2 | 0 | 1
8 | Inventar Management Seller | 2 | 2 | 0 | 1
9 | Database Cleanup | 1 | 1 | 0 |  | 1
10 | Order Status Progress-Bar | 1 | 1 | 0 | 1
11 | Inventar Seller Design | 1 | 1 | 0 | 1
12 | Inventar Seller Status | 1 | 1 | 0 | 1
13 | Finanzübersicht Seller | 2 | 2 | 0 | 1
n |  |  |  | 0
13 |  |  |  | 0 | 12 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol