## Tabelle1
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 2023-06-13 12:00
Group Number |  | 1 - Webshop
Participant 1 |  | Binh Duong Nguyen
Participant 2 |  | Duy Hiep Le
Participant 3 |  | Daniel Pfeifhofer
Participant 4 |  | Rafael Jeitler
Participant 5 |  | Elias Karner
Mentor |  | Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Refund Page Design | 3 | 3 | 0 | 1
2 | Refund Page Functionality | 2 | 2 | 0 | 1 |  | only formular
3 | Database Cleanup | 1 | 1 | 0 | 1
4 | Testing and Bugfixing | 5 | 5 | 0 | 1 |  | bugfixes
5 | Design Template Update | 2 | 2 | 0 | 1
6 | Design Cleanup | 2 | 2 | 0 | 1
7 | Mobile First Design | 4 | 4 | 0 | 1
8 | Video Presentation Conceptualization | 5 | 4 | -1 | 1 |  | meetup for video ideas
9 | Project Review | 2 | 2 | 0 | 1 |  | little review
n |  |  |  | 0
9 |  |  |  | -1 | 9 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol