## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 2024-04-18 18:11
Group Number |  | 1 - Webshop
Participant 1 |  | Binh Duong Nguyen
Participant 2 |  | Duy Hiep Le
Participant 3 |  | Daniel Pfeifhofer
Participant 4 |  | Rafael Jeitler
Participant 5 |  | Elias Karner
Mentor |  | Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Effort [h] | Delta [h] | Passed | failed | remarks
1 | Product Catalog | 2 | 2 | 0
2 | Product Categorisation | 3 | 2 | -1
3 | Products Sites Design | 5 | 5 | 0
4 | Inventory Management | 3 | 3 | 0
5 | Product Organisation | 3 | 3 | 0
6 | Color Grading | 1 | 1 | 0
7 | Change Profile Data | 2 | 2 | 0
8 | Mobile Design | 1 | 1 | 0
9 | Website Design Template | 3 | 3 | 0
10 | News Blog | 7 | 7 | 0
11 | Help Page | 1 | 1 | 0
12 | Impressum | 1 | 1 | 0
13 | Profile Hub for Users and Admins | 5 | 5 | 0
14 | Implement Searchbar | 2 | 2 | 0
… |  |  |  | 0
14 |  |  |  | -1 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol